## Initial Plan
Color Coding |  |  | Completed |  |  |  | SPRING 2020 SEMESTER
In Progress
[6 empty] | Week # | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[6 empty] | Date | 2020-01-30 | 2020-02-04 | 2020-02-18 | 2020-02-22 | 2020-02-28 | 2020-03-06 | 2020-03-20 | 2020-03-27 | 2020-04-03 | 2020-04-10 | 2020-04-17 | 2018-04-17 | 2018-04-24 | 2018-05-01 | 2018-05-08
Project Phase | Activity |  | Task Owner Name | Start Date | End Date | Progress %
Project Initiation | Discuss project proposals |  | ALL | 2020-01-28 | 2020-02-04 | 100%
| Confirm Project Team Roles |  | ALL | 2020-01-28 | 2020-02-04 | 100%
| Develop two business cases |  | Xing Chen | 2020-01-28 | 2020-02-04 | 100%
| Develop Project Initiation Document (PID) |  | Xing Chen, Mojin Zhang | 2020-02-04 | 2020-04-28 | 100%
| Produce initial Project Plan, RACI |  | Xing Chen, Mojin Zhang | 2018-02-13 | 2018-02-18 | 100%
MILESTONE 1: INITIAL PROJECT PLAN COMPLETED
Requirements Definition | Produce BRM diagram, define User Roles |  | Mojin Zhang | 2020-02-18 | 2020-02-25 | 100%
| Produce Context Diagram, Define System Interfaces |  | Saraluk Kaiwansakul, Sherin Dubey | 2020-02-18 | 2020-02-25 | 100%
| Agree to System Requirements types |  | Saraluk Kaiwansakul, Sherin Dubey | 2018-02-18 | 2020-02-25 | 100%
| Define Business Requirements |  | Mojin Zhang | 2020-02-25 | 2018-03-03 | 100%
| Define Functional Decomposition |  | Saraluk Kaiwansakul, Sherin Dubey | 2020-02-25 | 2020-03-03 | 100%
| Produce RCT document |  | Saraluk Kaiwansakul, Sherin Dubey | 2020-02-25 | 2020-03-03 | 100%
| Decide which features to implement this semester |  | ALL | 2020-03-03 | 2020-03-10 | 100%
| Use-Case Diagrams (UML) |  | Saraluk Kaiwansakul, Sherin Dubey | 2020-03-03 | 2020-03-10 | 100%
| Activity Diagram (UML) |  | Saraluk Kaiwansakul, Sherin Dubey | 2020-03-03 | 2020-03-10 | 100%
| Data-flow Diagrams (logical, physical) |  | Saraluk Kaiwansakul, Sherin Dubey | 2020-03-03 | 2020-03-24 | 100%
| Define functional requirements (User Stories) |  | Mojin Zhang | 2020-03-03 | 2020-03-10 | 100%
MILESTONE 2: REQUIREMENTS COMPLETED
| ER Diagrams (conceptual, logical) |  | Eric Chen, Xiaohan Yu | 2020-03-16 | 2020-03-24 | 100%
| Table Specifications (Data Dictionary) |  | Eric Chen, Xiaohan Yu | 2020-03-16 | 2020-03-24 | 100%
| Architecture design (2 diagrams - Logical, process views) |  | Te-Yi Tsai, Eric Chen, Xiaohan Yu | 2020-03-24 | 2020-03-31 | 100%
| Class Diagrams |  | Te-Yi Tsai | 2020-03-31 | 2020-04-07 | 100%
| Sequence Diagrams |  | Te-Yi Tsai | 2020-03-31 | 2020-04-07 | 100%
| System Interface Design |  | Te-Yi Tsai | 2020-03-31 | 2020-04-07 | 100%
| User interface design |  | Te-Yi Tsai | 2020-03-31 | 2020-04-07 | 100%
MILESTONE 3: DESIGN COMPLETED
Code | 01.01 Account Creation and Modification |  | Te-Yi Tsai | 2020-03-31 | 2020-05-05 | 100%
| - Different signup pages for customer and restaurant |  | Te-Yi Tsai | 2020-03-31 | 2020-05-05 | 100%
| - Login page for both customer and restaurant |  | Mojin Zhang | 2020-03-31 | 2020-05-05 | 100%
| - Edit function on personal info: username, email, password, phone number, etc. |  | Te-Yi Tsai | 2020-03-31 | 2020-05-05 | 100%
| 01.02 Account Authentication |  | Te-Yi Tsai | 2020-03-31 | 2020-05-05 | 100%
| - Customer side: account validation alert |  | Te-Yi Tsai | 2020-03-31 | 2020-05-05 | 100%
| 01.03 Account Summary |  | Te-Yi Tsai | 2020-03-31 | 2020-05-05 | 100%
| - Customer profile page |  | Saraluk Kaiwansakul | 2020-03-31 | 2020-05-05 | 100%
| - Restaurant profile page |  | Saraluk Kaiwansakul | 2020-03-31 | 2020-05-05 | 100%
| Connect with backend database |  | Eric Chen | 2020-03-31 | 2020-05-05 | 100%
MILESTONE 4: CODING COMPLETED
Integration & Testing | Test Plan document |  | Qiang Xu | 2020-04-07 | 2020-04-14 | 100%
| Test design, test cases |  | Qiang Xu | 2020-04-07 | 2020-04-21 | 100%
| Execute Test Cases |  | Qiang Xu | 2020-04-07 | 2020-04-21 | 100%
| Evaluate feature to be tested and anaylze the test results |  | Qiang Xu | 2020-04-07 | 2020-04-21 | 100%
| subtasks: | 01.01 account creation and modification | Qiang Xu | 2020-04-07 | 2020-04-21 | 100%
|  | 01.02 account authentication | Qiang Xu | 2020-04-07 | 2020-04-21 | 100%
|  | 01.03 account summary | Qiang Xu | 2020-04-07 | 2020-04-21 | 100%
MILESTONE 5: TESTING COMPLETED
Project Presentation | Prepare Application Demo for the Presentation |  | ALL | 2020-04-21 | 2020-05-01 | 100%